## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
User Login Screen | Login screen that allows users to enter email and password. Supports Google OAuth2 login, includes links for user registration and password recovery. | 1 | https://gitlab.com/liteflow/swp391/-/issues/1 | Closed | Đức Giang | 2025-09-20 | 2025-09-25 | iter1 | WP, 3_Done | User Login
Write SRS for User Login screen | Write detailed functional specification for the User Login screen including authentication flow, OAuth2 integration, and password recovery links. | 2 | https://gitlab.com/liteflow/swp391/-/issues/2 | Closed | Đức Giang | 2025-09-20 | 2025-09-22 | iter1 | Task, 3_Done | User Login
Write SDS for User Login screen | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the User Login screen including AuthService, LoginServlet, and JWT token management. | 3 | https://gitlab.com/liteflow/swp391/-/issues/3 | Closed | Đức Giang | 2025-09-22 | 2025-09-24 | iter1 | Task, 3_Done | User Login
Write Code for User Login screen | Code & Unit test for the User Login screen including authentication logic, OAuth2 callback handling, and session management. | 4 | https://gitlab.com/liteflow/swp391/-/issues/4 | Closed | Đức Giang | 2025-09-24 | 2025-09-25 | iter1 | Task, 3_Done | User Login
User Registration Screen | New account registration screen requiring email, password, password confirmation and basic information. Sends OTP verification email after registration. | 5 | https://gitlab.com/liteflow/swp391/-/issues/5 | Closed | Đức Giang | 2025-09-20 | 2025-09-26 | iter1 | WP, 3_Done | User Registration
Write Code for User Registration | Code & Unit test for User Registration screen including validation, email service integration, and OTP generation. | 6 | https://gitlab.com/liteflow/swp391/-/issues/6 | Closed | Đức Giang | 2025-09-22 | 2025-09-26 | iter1 | Task, 3_Done | User Registration
Password Recovery Screen | Forgot password screen that allows users to enter email to receive OTP via email. After OTP verification, users can reset their password. | 7 | https://gitlab.com/liteflow/swp391/-/issues/7 | Closed | Đức Giang | 2025-09-20 | 2025-09-27 | iter1 | WP, 3_Done | Password Recovery
Two-Factor Authentication (2FA) | Two-factor authentication system using TOTP. Users need to enter a 6-digit code from authenticator app after login to upgrade their session. | 8 | https://gitlab.com/liteflow/swp391/-/issues/8 | Closed | Đức Giang | 2025-09-25 | 2025-10-01 | iter1 | WP, 3_Done | 2FA Authentication
OAuth2 Google Login Integration | Google account login integration. Handles Google OAuth2 callback, creates or updates user information and grants access. | 9 | https://gitlab.com/liteflow/swp391/-/issues/9 | Closed | Đức Giang | 2025-09-25 | 2025-10-02 | iter1 | WP, 3_Done | OAuth2 Login
Session Management with JWT | Session management using JWT tokens. Handles timeout, refresh token and checks access permissions based on user roles. | 10 | https://gitlab.com/liteflow/swp391/-/issues/10 | Closed | Đức Giang | 2025-09-25 | 2025-10-03 | iter1 | WP, 3_Done | Session Management
Cashier Interface Screen | Main cashier interface that allows managing tables/rooms, browsing menu, creating orders, adding/removing items, calculating totals (including tax and discounts). Integrated with inventory and kitchen systems. | 11 | https://gitlab.com/liteflow/swp391/-/issues/11 | Closed | Đức Giang | 2025-09-20 | 2025-09-28 | iter1 | WP, 3_Done | Cashier Interface
Write SRS for Cashier Interface | Write detailed functional specification for Cashier Interface including table management, order creation workflow, and payment processing. | 12 | https://gitlab.com/liteflow/swp391/-/issues/12 | Closed | Đức Giang | 2025-09-20 | 2025-09-22 | iter1 | Task, 3_Done | Cashier Interface
Write Code for Cashier Interface | Code & Unit test for Cashier Interface including CashierServlet, order management logic, and real-time inventory integration. | 13 | https://gitlab.com/liteflow/swp391/-/issues/13 | Closed | Đức Giang | 2025-09-24 | 2025-09-28 | iter1 | Task, 3_Done | Cashier Interface
Table/Room Management | Manage table/room status (empty, serving, reserved). Displays table list with real-time status, allows selecting table to create new order. | 14 | https://gitlab.com/liteflow/swp391/-/issues/14 | Closed | Đức Giang | 2025-09-22 | 2025-09-29 | iter1 | WP, 3_Done | Table Management
Order Creation Function | Create new order: select table, add items from menu, confirm quantity, check inventory, calculate price. Automatically deducts inventory and notifies kitchen when order is created. | 15 | https://gitlab.com/liteflow/swp391/-/issues/15 | Closed | Đức Giang | 2025-09-24 | 2025-09-30 | iter1 | WP, 3_Done | Order Creation
Order Modification Function | Modify existing order: add/remove items, change quantity, apply discounts. Automatically recalculates total and rechecks inventory. | 16 | https://gitlab.com/liteflow/swp391/-/issues/16 | Closed | Đức Giang | 2025-09-28 | 2025-10-04 | iter2 | WP, 3_Done | Order Modification
Payment Processing Function | Process order payment: select payment method (cash, card, transfer), apply discounts, print invoice, close table session and update revenue. | 17 | https://gitlab.com/liteflow/swp391/-/issues/17 | Closed | Đức Giang | 2025-09-28 | 2025-10-05 | iter2 | WP, 3_Done | Payment Processing
Split Bill Function | Split bill for multiple customers: divide items by group, calculate each portion separately, process independent payment for each portion. | 18 | https://gitlab.com/liteflow/swp391/-/issues/18 | Closed | Đức Giang | 2025-09-28 | 2025-10-06 | iter2 | WP, 3_Done | Split Bill
Order History Screen | View order history: list of created, paid, and cancelled orders. Filter by date, table, status. Display details of each order. | 19 | https://gitlab.com/liteflow/swp391/-/issues/19 | Closed | Đức Giang | 2025-09-28 | 2025-10-07 | iter2 | WP, 3_Done | Order History
Invoice Printing Function | Print invoice after payment: displays order information, items, prices, tax, total. Supports direct printing or PDF export. | 20 | https://gitlab.com/liteflow/swp391/-/issues/20 | Closed | Đức Giang | 2025-09-28 | 2025-10-08 | iter2 | WP, 3_Done | Invoice Printing
Kitchen Display System | Kitchen order display system: receives orders from cashier, displays pending order queue, sorts by priority. Updates status in real-time. | 21 | https://gitlab.com/liteflow/swp391/-/issues/21 | Closed | Đức Giang | 2025-09-28 | 2025-10-09 | iter2 | WP, 3_Done | Kitchen Display
Order Status Workflow | Order status update workflow: Pending → Preparing → Ready → Served. Each status is updated by kitchen staff and automatically notifies cashier. | 22 | https://gitlab.com/liteflow/swp391/-/issues/22 | Closed | Đức Giang | 2025-09-28 | 2025-10-10 | iter2 | WP, 3_Done | Order Status
Multi-Station Routing | Distribute orders to different kitchen stations (appetizer, main course, dessert) based on dish type. Each station only displays items belonging to that station. | 23 | https://gitlab.com/liteflow/swp391/-/issues/23 | Closed | Đức Giang | 2025-09-28 | 2025-10-11 | iter2 | WP, 3_Done | Multi-Station
Priority Order Handling | Handle priority orders: mark important orders, sort to top of list, display special alerts for quick processing. | 24 | https://gitlab.com/liteflow/swp391/-/issues/24 | Closed | Đức Giang | 2025-09-28 | 2025-10-12 | iter2 | WP, 3_Done | Priority Orders
Product Catalog Management | Product catalog management: add, edit, delete products. Manage product variants (size, options), images, descriptions. Organize by room/table. | 25 | https://gitlab.com/liteflow/swp391/-/issues/25 | Closed | Đức Giang | 2025-09-25 | 2025-10-13 | iter2 | WP, 3_Done | Product Catalog
Write Code for Product Catalog | Code & Unit test for Product Catalog including ProductServlet, product CRUD operations, and image upload functionality. | 26 | https://gitlab.com/liteflow/swp391/-/issues/26 | Closed | Đức Giang | 2025-10-10 | 2025-10-13 | iter2 | Task, 3_Done | Product Catalog
Stock Level Tracking | Track stock levels: displays current inventory quantity, import/export history, low stock alerts. Automatically updates when orders are created or goods are received. | 27 | https://gitlab.com/liteflow/swp391/-/issues/27 | Closed | Đức Giang | 2025-09-25 | 2025-10-14 | iter2 | WP, 3_Done | Stock Tracking
Low Stock Alerts System | Low stock alert system: automatically sends notifications when inventory quantity falls below threshold. Displays list of products that need restocking. | 28 | https://gitlab.com/liteflow/swp391/-/issues/28 | Closed | Đức Giang | 2025-09-25 | 2025-10-15 | iter2 | WP, 3_Done | Low Stock Alerts
Price Management Function | Product price management: set base price, price by size/variant, apply promotional prices, price change history. | 29 | https://gitlab.com/liteflow/swp391/-/issues/29 | Closed | Đức Giang | 2025-09-25 | 2025-10-16 | iter2 | WP, 3_Done | Price Management
Excel Import/Export Function | Import/export product data via Excel files: import product list from Excel, export product list and inventory to Excel for reporting. | 30 | https://gitlab.com/liteflow/swp391/-/issues/30 | Closed | Đức Giang | 2025-09-25 | 2025-10-17 | iter2 | WP, 3_Done | Excel Import/Export
Room/Table Inventory Management | Manage inventory by room/table: organize products by area, manage separate inventory for each room/table if needed. | 31 | https://gitlab.com/liteflow/swp391/-/issues/31 | Closed | Đức Giang | 2025-09-25 | 2025-10-18 | iter2 | WP, 3_Done | Room Inventory
Employee List Screen | Employee list: displays basic information, roles, work status. Search, filter by role, sort. Allows viewing details, editing and deleting employees. | 32 | https://gitlab.com/liteflow/swp391/-/issues/32 | Closed | Đức Giang | 2025-09-25 | 2025-10-19 | iter2 | WP, 3_Done | Employee List
Employee Profile Management | Employee profile management: personal information, contact details, roles, access permissions. Create new, update, deactivate employee accounts. | 33 | https://gitlab.com/liteflow/swp391/-/issues/33 | Closed | Đức Giang | 2025-09-25 | 2025-10-20 | iter2 | WP, 3_Done | Employee Profile
Attendance Tracking System | Attendance tracking: employees clock in/out, view attendance history, statistics of working hours. Manual attendance management for forgotten cases. | 34 | https://gitlab.com/liteflow/swp391/-/issues/34 | Closed | Đức Giang | 2025-09-25 | 2025-10-21 | iter2 | WP, 3_Done | Attendance
Schedule Management Screen | Schedule management: create work shift schedule, assign employees to shifts, view schedule by week/month. Allows editing, swapping shifts between employees. | 35 | https://gitlab.com/liteflow/swp391/-/issues/35 | Closed | Đức Giang | 2025-09-25 | 2025-10-22 | iter2 | WP, 3_Done | Schedule
Paysheet Generation Function | Paysheet generation: calculate salary based on working hours, shifts, allowances. Export paysheet, print or email to employees. | 36 | https://gitlab.com/liteflow/swp391/-/issues/36 | Closed | Đức Giang | 2025-09-25 | 2025-10-23 | iter2 | WP, 3_Done | Paysheet
Role-Based Access Control | Role-based access control: assign roles to employees (Admin, Manager, Cashier, Kitchen Staff, Employee), manage access permissions to functions by role. | 37 | https://gitlab.com/liteflow/swp391/-/issues/37 | Closed | Đức Giang | 2025-09-25 | 2025-10-24 | iter2 | WP, 3_Done | RBAC
Supplier Management Screen | Supplier management: supplier list, contact information, transaction history. Add, edit, delete suppliers. Rate and add notes about suppliers. | 38 | https://gitlab.com/liteflow/swp391/-/issues/38 | Closed | Đức Giang | 2025-09-25 | 2025-10-25 | iter3 | WP, 3_Done | Supplier Management
Purchase Order (PO) Creation | Create purchase order: select supplier, add products to purchase, quantity, price. Send purchase order, track status (Draft, Sent, Confirmed, Received). | 39 | https://gitlab.com/liteflow/swp391/-/issues/39 | Closed | Đức Giang | 2025-09-25 | 2025-10-26 | iter3 | WP, 3_Done | PO Creation
PO Tracking Function | Purchase order tracking: list of POs, status of each PO, update history. Filter by supplier, date, status. View details of each PO. | 40 | https://gitlab.com/liteflow/swp391/-/issues/40 | Closed | Đức Giang | 2025-09-25 | 2025-10-27 | iter3 | WP, 3_Done | PO Tracking
Goods Receipt Function | Goods receipt: record received goods from supplier, match with PO, automatically update inventory. Check quality, quantity, add notes if there are discrepancies. | 41 | https://gitlab.com/liteflow/swp391/-/issues/41 | Closed | Đức Giang | 2025-09-25 | 2025-10-28 | iter3 | WP, 3_Done | Goods Receipt
Invoice Matching Function | Invoice matching: match supplier invoices with PO and goods receipt. Verify amount, quantity, price. Approve invoices for payment. | 42 | https://gitlab.com/liteflow/swp391/-/issues/42 | Closed | Đức Giang | 2025-09-25 | 2025-10-29 | iter3 | WP, 3_Done | Invoice Matching
Procurement Dashboard | Procurement dashboard: overview of purchase orders, procurement costs, suppliers, statistics charts. Analyze procurement trends and costs. | 43 | https://gitlab.com/liteflow/swp391/-/issues/43 | Closed | Đức Giang | 2025-09-25 | 2025-10-30 | iter3 | WP, 3_Done | Procurement Dashboard
Main Dashboard Screen | Main dashboard: displays real-time business metrics (revenue, orders, customers), trend charts, important notifications. Overview of restaurant operational status. | 44 | https://gitlab.com/liteflow/swp391/-/issues/44 | Closed | Đức Giang | 2025-09-25 | 2025-10-31 | iter3 | WP, 3_Done | Main Dashboard
Sales Performance Analytics | Sales performance: revenue statistics by day/week/month, period comparison, top-selling products, sales trend charts. | 45 | https://gitlab.com/liteflow/swp391/-/issues/45 | Closed | Đức Giang | 2025-09-25 | 2025-11-01 | iter3 | WP, 3_Done | Sales Performance
Inventory Status Analytics | Inventory status: overview of product quantity, inventory value, products running low, inventory distribution chart by category. | 46 | https://gitlab.com/liteflow/swp391/-/issues/46 | Closed | Đức Giang | 2025-09-25 | 2025-11-02 | iter3 | WP, 3_Done | Inventory Status
Employee Performance Analytics | Employee performance: statistics of working hours, orders processed, performance evaluation. Compare between employees, productivity charts. | 47 | https://gitlab.com/liteflow/swp391/-/issues/47 | Closed | Đức Giang | 2025-09-25 | 2025-11-03 | iter3 | WP, 3_Done | Employee Performance
Revenue Report Function | Revenue report: export detailed revenue report by time period, by product, by employee. Supports Excel or PDF export. | 48 | https://gitlab.com/liteflow/swp391/-/issues/48 | Closed | Đức Giang | 2025-09-25 | 2025-11-04 | iter3 | WP, 3_Done | Revenue Report
Header & Navigation Component | Common header and navigation bar for all pages: role-based menu, notifications, user information, logout. Responsive design for mobile and desktop. | 49 | https://gitlab.com/liteflow/swp391/-/issues/49 | Closed | Đức Giang | 2025-09-20 | 2025-11-05 | iter1 | WP, 3_Done | Header & Navigation
Notification System | Notification system: displays real-time notifications (new orders, low stock, work schedule), notification bell, list of unread notifications. | 50 | https://gitlab.com/liteflow/swp391/-/issues/50 | Closed | Đức Giang | 2025-09-25 | 2025-11-06 | iter3 | WP, 3_Done | Notification System
Access Control Filters | Access control: authentication and authorization filters, redirect to login page if not logged in, display access denied page if no permission. | 51 | https://gitlab.com/liteflow/swp391/-/issues/51 | Closed | Đức Giang | 2025-09-20 | 2025-11-07 | iter1 | WP, 3_Done | Access Control
Error Handling System | Error handling: 404, 500 error pages, display user-friendly error messages, log errors for debugging. Handle exceptions and rollback transactions on errors. | 52 | https://gitlab.com/liteflow/swp391/-/issues/52 | Closed | Đức Giang | 2025-09-20 | 2025-11-08 | iter1 | WP, 3_Done | Error Handling
Integrate Authentication with POS | Integrate the Authentication module with POS system to ensure proper access control and session management for cashier operations. | 53 | https://gitlab.com/liteflow/swp391/-/issues/53 | Closed | Đức Giang | 2025-09-25 | 2025-09-30 | iter1 | Task, 3_Done | Integration
Integrate POS with Kitchen System | Integrate POS system with Kitchen Display System to enable real-time order notifications and status updates. | 54 | https://gitlab.com/liteflow/swp391/-/issues/54 | Closed | Đức Giang | 2025-09-30 | 2025-10-09 | iter2 | Task, 3_Done | Integration
Integrate Inventory with POS | Integrate Inventory Management with POS system to enable automatic stock deduction and low stock alerts when orders are created. | 55 | https://gitlab.com/liteflow/swp391/-/issues/55 | Closed | Đức Giang | 2025-10-13 | 2025-10-18 | iter2 | Task, 3_Done | Integration
Integrate Procurement with Inventory | Integrate Procurement system with Inventory Management to automatically update stock levels when goods are received. | 56 | https://gitlab.com/liteflow/swp391/-/issues/56 | Closed | Đức Giang | 2025-10-25 | 2025-10-28 | iter3 | Task, 3_Done | Integration
Fix: OAuth2 callback redirect issue | OAuth2 Google login callback redirects to wrong URL after authentication. Need to fix redirect URI configuration and session handling. | 57 | https://gitlab.com/liteflow/swp391/-/issues/57 | Closed | Đức Giang | 2025-10-02 | 2025-10-03 | iter1 | Defect, 3_Done | OAuth2 Login
Fix: Inventory not updating on order | Inventory stock level is not automatically deducted when order is created. Need to fix OrderService to properly update inventory. | 58 | https://gitlab.com/liteflow/swp391/-/issues/58 | Closed | Đức Giang | 2025-09-30 | 2025-10-02 | iter2 | Defect, 3_Done | Order Creation
Fix: Kitchen notification not working | Kitchen staff are not receiving real-time notifications when new orders are created. Need to fix WebSocket connection and notification service. | 59 | https://gitlab.com/liteflow/swp391/-/issues/59 | Closed | Đức Giang | 2025-10-09 | 2025-10-11 | iter2 | Defect, 3_Done | Kitchen Display
Fix: Excel import validation error | Excel import for products fails when file contains invalid data. Need to add proper validation and error handling for Excel import functionality. | 60 | https://gitlab.com/liteflow/swp391/-/issues/60 | Closed | Đức Giang | 2025-10-17 | 2025-10-18 | iter2 | Defect, 3_Done | Excel Import/Export
Fix: Payment calculation incorrect | Payment total calculation is incorrect when applying multiple discounts. Need to fix discount calculation logic in PaymentService. | 61 | https://gitlab.com/liteflow/swp391/-/issues/61 | Closed | Đức Giang | 2025-10-05 | 2025-10-06 | iter2 | Defect, 3_Done | Payment Processing
Fix: Session timeout too short | User sessions expire too quickly causing users to be logged out frequently. Need to adjust JWT token expiration time and session timeout settings. | 62 | https://gitlab.com/liteflow/swp391/-/issues/62 | Closed | Đức Giang | 2025-10-03 | 2025-10-05 | iter1 | Defect, 3_Done | Session Management
Missing: User Register link on Login | The User Register link is missing on the Login screen mockup. Need to add registration link to login page as per SRS document. | 63 | https://gitlab.com/liteflow/swp391/-/issues/63 | Closed | Đức Giang | 2025-09-25 | 2025-09-26 | iter1 | Defect, 3_Done | User Login
Missing: Forgot Password link | The Forgot Password link is not visible on the Login screen. Need to add forgot password link to improve user experience. | 64 | https://gitlab.com/liteflow/swp391/-/issues/64 | Closed | Đức Giang | 2025-09-25 | 2025-09-27 | iter1 | Defect, 3_Done | User Login
Missing: Low stock alert notification | Low stock alerts are not being sent to managers. Need to implement notification service for low stock alerts. | 65 | https://gitlab.com/liteflow/swp391/-/issues/65 | Closed | Đức Giang | 2025-10-15 | 2025-10-16 | iter2 | Defect, 3_Done | Low Stock Alerts