## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen / Function | Feature | Role | Screen/Function Description | In Charge | Status | Completion Date
1 | User Login | Authentication | All Users | Login screen that allows users to enter email and password. Supports Google OAuth2 login, includes links for user registration and password recovery. | Đức Giang | Done | 2025-09-25
2 | User Registration | Authentication | Guest | New account registration screen requiring email, password, password confirmation and basic information. Sends OTP verification email after registration. | Đức Giang | Done | 2025-09-26
3 | Password Recovery | Authentication | Guest | Forgot password screen that allows users to enter email to receive OTP via email. After OTP verification, users can reset their password. | Đức Giang | Done | 2025-09-27
4 | Two-Factor Authentication (2FA) | Authentication | All Users | Two-factor authentication system using TOTP. Users need to enter a 6-digit code from authenticator app after login to upgrade their session. | Đức Giang | Done | 2025-10-01
5 | OAuth2 Google Login | Authentication | All Users | Google account login integration. Handles Google OAuth2 callback, creates or updates user information and grants access. | Đức Giang | Done | 2025-10-02
6 | Session Management | Authentication | All Users | Session management using JWT tokens. Handles timeout, refresh token and checks access permissions based on user roles. | Đức Giang | Done | 2025-10-03
POINT OF SALE (POS) SYSTEM MODULE
7 | Cashier Interface | POS | Cashier | Main cashier interface that allows managing tables/rooms, browsing menu, creating orders, adding/removing items, calculating totals (including tax and discounts). Integrated with inventory and kitchen systems. | Đức Giang | Done | 2025-09-28
8 | Table/Room Management | POS | Cashier, Manager | Manage table/room status (empty, serving, reserved). Displays table list with real-time status, allows selecting table to create new order. | Đức Giang | Done | 2025-09-29
9 | Order Creation | POS | Cashier | Create new order: select table, add items from menu, confirm quantity, check inventory, calculate price. Automatically deducts inventory and notifies kitchen when order is created. | Đức Giang | Done | 2025-09-30
10 | Order Modification | POS | Cashier | Modify existing order: add/remove items, change quantity, apply discounts. Automatically recalculates total and rechecks inventory. | Đức Giang | Done | 2025-10-04
11 | Payment Processing | POS | Cashier | Process order payment: select payment method (cash, card, transfer), apply discounts, print invoice, close table session and update revenue. | Đức Giang | Done | 2025-10-05
12 | Split Bill | POS | Cashier | Split bill for multiple customers: divide items by group, calculate each portion separately, process independent payment for each portion. | Đức Giang | Done | 2025-10-06
13 | Order History | POS | Cashier, Manager | View order history: list of created, paid, and cancelled orders. Filter by date, table, status. Display details of each order. | Đức Giang | Done | 2025-10-07
14 | Invoice Printing | POS | Cashier | Print invoice after payment: displays order information, items, prices, tax, total. Supports direct printing or PDF export. | Đức Giang | Done | 2025-10-08
KITCHEN MANAGEMENT MODULE
15 | Kitchen Display System | Kitchen | Kitchen Staff | Kitchen order display system: receives orders from cashier, displays pending order queue, sorts by priority. Updates status in real-time. | Đức Giang | Done | 2025-10-09
16 | Order Status Workflow | Kitchen | Kitchen Staff | Order status update workflow: Pending → Preparing → Ready → Served. Each status is updated by kitchen staff and automatically notifies cashier. | Đức Giang | Done | 2025-10-10
17 | Multi-Station Routing | Kitchen | Kitchen Staff | Distribute orders to different kitchen stations (appetizer, main course, dessert) based on dish type. Each station only displays items belonging to that station. | Đức Giang | Done | 2025-10-11
18 | Priority Order Handling | Kitchen | Kitchen Staff | Handle priority orders: mark important orders, sort to top of list, display special alerts for quick processing. | Đức Giang | Done | 2025-10-12
INVENTORY MANAGEMENT MODULE
19 | Product Catalog | Inventory | Admin, Manager | Product catalog management: add, edit, delete products. Manage product variants (size, options), images, descriptions. Organize by room/table. | Đức Giang | Done | 2025-10-13
20 | Stock Level Tracking | Inventory | Admin, Manager | Track stock levels: displays current inventory quantity, import/export history, low stock alerts. Automatically updates when orders are created or goods are received. | Đức Giang | Done | 2025-10-14
21 | Low Stock Alerts | Inventory | Admin, Manager | Low stock alert system: automatically sends notifications when inventory quantity falls below threshold. Displays list of products that need restocking. | Đức Giang | Done | 2025-10-15
22 | Price Management | Inventory | Admin, Manager | Product price management: set base price, price by size/variant, apply promotional prices, price change history. | Đức Giang | Done | 2025-10-16
23 | Excel Import/Export | Inventory | Admin, Manager | Import/export product data via Excel files: import product list from Excel, export product list and inventory to Excel for reporting. | Đức Giang | Done | 2025-10-17
24 | Room/Table Inventory | Inventory | Admin, Manager | Manage inventory by room/table: organize products by area, manage separate inventory for each room/table if needed. | Đức Giang | Done | 2025-10-18
EMPLOYEE & HR MANAGEMENT MODULE
25 | Employee List | HR | Admin, Manager | Employee list: displays basic information, roles, work status. Search, filter by role, sort. Allows viewing details, editing and deleting employees. | Đức Giang | Done | 2025-10-19
26 | Employee Profile | HR | Admin, Manager | Employee profile management: personal information, contact details, roles, access permissions. Create new, update, deactivate employee accounts. | Đức Giang | Done | 2025-10-20
27 | Attendance Tracking | HR | Admin, Manager | Attendance tracking: employees clock in/out, view attendance history, statistics of working hours. Manual attendance management for forgotten cases. | Đức Giang | Done | 2025-10-21
28 | Schedule Management | HR | Admin, Manager | Schedule management: create work shift schedule, assign employees to shifts, view schedule by week/month. Allows editing, swapping shifts between employees. | Đức Giang | Done | 2025-10-22
29 | Paysheet Generation | HR | Admin, Manager | Paysheet generation: calculate salary based on working hours, shifts, allowances. Export paysheet, print or email to employees. | Đức Giang | Done | 2025-10-23
30 | Role-Based Access | HR | Admin | Role-based access control: assign roles to employees (Admin, Manager, Cashier, Kitchen Staff, Employee), manage access permissions to functions by role. | Đức Giang | Done | 2025-10-24
PROCUREMENT SYSTEM MODULE
31 | Supplier Management | Procurement | Admin, Manager | Supplier management: supplier list, contact information, transaction history. Add, edit, delete suppliers. Rate and add notes about suppliers. | Đức Giang | Done | 2025-10-25
32 | Purchase Order (PO) Creation | Procurement | Admin, Manager | Create purchase order: select supplier, add products to purchase, quantity, price. Send purchase order, track status (Draft, Sent, Confirmed, Received). | Đức Giang | Done | 2025-10-26
33 | PO Tracking | Procurement | Admin, Manager | Purchase order tracking: list of POs, status of each PO, update history. Filter by supplier, date, status. View details of each PO. | Đức Giang | Done | 2025-10-27
34 | Goods Receipt | Procurement | Admin, Manager | Goods receipt: record received goods from supplier, match with PO, automatically update inventory. Check quality, quantity, add notes if there are discrepancies. | Đức Giang | Done | 2025-10-28
35 | Invoice Matching | Procurement | Admin, Manager | Invoice matching: match supplier invoices with PO and goods receipt. Verify amount, quantity, price. Approve invoices for payment. | Đức Giang | Done | 2025-10-29
36 | Procurement Dashboard | Procurement | Admin, Manager | Procurement dashboard: overview of purchase orders, procurement costs, suppliers, statistics charts. Analyze procurement trends and costs. | Đức Giang | Done | 2025-10-30
DASHBOARD & ANALYTICS MODULE
37 | Main Dashboard | Analytics | Admin, Manager | Main dashboard: displays real-time business metrics (revenue, orders, customers), trend charts, important notifications. Overview of restaurant operational status. | Đức Giang | Done | 2025-10-31
38 | Sales Performance | Analytics | Admin, Manager | Sales performance: revenue statistics by day/week/month, period comparison, top-selling products, sales trend charts. | Đức Giang | Done | 2025-11-01
39 | Inventory Status | Analytics | Admin, Manager | Inventory status: overview of product quantity, inventory value, products running low, inventory distribution chart by category. | Đức Giang | Done | 2025-11-02
40 | Employee Performance | Analytics | Admin, Manager | Employee performance: statistics of working hours, orders processed, performance evaluation. Compare between employees, productivity charts. | Đức Giang | Done | 2025-11-03
41 | Revenue Report | Analytics | Admin, Manager | Revenue report: export detailed revenue report by time period, by product, by employee. Supports Excel or PDF export. | Đức Giang | Done | 2025-11-04
COMMON FEATURES
42 | Header & Navigation | Common | All Users | Common header and navigation bar for all pages: role-based menu, notifications, user information, logout. Responsive design for mobile and desktop. | Đức Giang | Done | 2025-11-05
43 | Notification System | Common | All Users | Notification system: displays real-time notifications (new orders, low stock, work schedule), notification bell, list of unread notifications. | Đức Giang | Done | 2025-11-06
44 | Access Control | Common | All Users | Access control: authentication and authorization filters, redirect to login page if not logged in, display access denied page if no permission. | Đức Giang | Done | 2025-11-07
45 | Error Handling | Common | All Users | Error handling: 404, 500 error pages, display user-friendly error messages, log errors for debugging. Handle exceptions and rollback transactions on errors. | Đức Giang | Done | 2025-11-08